Formal Solicitation Minimal Timeline – ITB-C

Formal solicitation drafts (Invitation to Bid - Construction) require the following number of days to allow for Procurement Services review and processing prior to issue.

| Solicitation Minimal Timeline | Recommended number of days for procurement review and processing | Minimum number of days for procurement review and processing | Related PPS Public Contracting Rule or Oregon Revised Statute | Reasoning / References |
| --- | --- | --- | --- | --- |
| ITB-C |  |  |  |  |
| Documents to Purchasing and ready for issue | 3 business days | 2 business days | Documents comply with rule and statute upon submission to Purchasing and Contracting | Allow for review for PPS Public Contracting Rules compliance, advertisement, posting of solicitation, posting of any plans/drawings. Procurement and department generally review multiple versions prior to issue. |
| From date of solicitation issue to Pre-Bid Conference | 10 calendar days | 7 calendar days (not counting holidays) | PPS-47-0420 (3) “reasonable time” | Allow time for adequate vendor review, determination by vendor whether work scope is a “match” for their company; allow time for vendors to adjust their schedules to attend. Allows adequate time for advertising and outreach. |
| From date of Pre-Bid Conference to last day for vendor questions/substitution requests | 5 business days | 3 business days |  | Allows vendors time to get questions and substitution requests together and maximizes competition. |
| From the last day for vendor questions to final addendum | 3 business days | 2 business days | . | Allows adequate time for compiling questions, obtaining answers, creating/proofreading the addendum, and posting to ORPIN. More time may be required if posting new or altered plans/drawings |
| Final Addendum to Bids Due | 5 calendar days | 72 hours. Must state in solicitation | PPS-47-0430 ITB-C: PPS-49-0250 | Allow adequate time for vendor review and feedback, consideration of any changes which would affect a proposal. The more significant the amended change, the greater the number of days necessary. |
| Date of Issue to Due Date | 2-4 weeks | 14 calendar days (close only T, W, TH) between 2:00PM – 5:00PM | PPS-49-0200 (G) | All of the above |
| 1st Tier Subcontractor, GFE Form 1 and GFE Form 2 for Purchasing Review | 72 hours | 48 hours |  | Allow time for P&C to perform responsiveness check |
| Recommendation to Award | 24 hours | ASAP |  | Following receipt of responsibility check |
| Notice of Intent to Award | 24 hours | ASAP |  | Following receipt of signed recommendation to award |