Formal Solicitation Minimal Timeline – RFP

Formal solicitation drafts (Request for Proposals) require the following number of days to allow for Purchasing & Contracting to review and process prior to issue.

| Solicitation Minimal Timeline | Recommended number of days for procurement review and processing | Minimum number of days for procurement review and processing | Related PPS Public Contracting Rule or Oregon Revised Statute | Reasoning / References |
| --- | --- | --- | --- | --- |
| Purchasing & Contracting and department generally review multiple versions prior to issue. |  |  |  |  |
| Documents to Purchasing and ready for issue. Including list of evaluation committee members. | 3 business days | 2 business days | Documents comply with rule and statute upon submission to Purchasing and Contracting | Time required for Purchasing & Contracting advertisement, posting of the solicitation and performing outreach to potential proposers. |
| From date of solicitation issue to Pre-Proposal Conference | 10 business days | 5 business days | PPS-47-0420 (3) “reasonable time” | Allow time for adequate vendor review, determination by vendor whether work scope is a “match” for their company; allow time for vendors to adjust their schedules to attend. Allows adequate time for advertising and outreach. |
| From date of Pre-Proposal Conference to last day for vendor questions/substitution requests | 8 business days | 5 business days |  | Allows vendors time to get questions and substitution requests together and maximizes competition. |
| From the last day for vendor questions to final addendum | 3 business days | 2 business days | . | Allows adequate time for compiling questions, obtaining answers, creating/proofreading the addendum, and posting to ORPIN. More time may be required if posting new or altered plans/drawings |
| Final Addendum to Proposals Due | 5 calendar days | 72 hours. Must state in solicitation | PPS-47-0430 | Allow adequate time for vendor review and feedback, consideration of any changes which would affect a proposal. The more significant the amended change, the greater the number of days necessary. |
| Date of Issue to Due Date | 3-4 weeks | 14 calendar days |  | All of the above |
| Due Date to Evaluation Kick-off meeting | 3 business days | 1 business day |  | Allows time for responsiveness check and preparation of the packets |
| Kick-off meeting to optional evaluation team meeting to discuss proposals |  |  |  | Solicitation manager requests an additional meeting to discuss the evaluation |
| Kick-off meeting to evaluation due | 5 business days | 3 business days |  |  |
| Evaluations due to Final evaluation team meeting | 1 business day | 1 business day |  |  |
| Evaluation complete to Recommendation to Award | 24 hours | ASAP |  | Following receipt of responsibility check |
| Notice of Intent to Award | 24 hours | ASAP |  | Following receipt of signed recommendation to award |